## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | Alin | 2020-06-15 | 2020-07-17 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Sarah &Bayan |  | 2020-06-15 | 2020-06-07 | 10 | Complete
| design registeration and login page |  | Sarah |  | 2020-06-15 | 2020-06-17 | 3 | Complete
| design vacation's page |  | Sarah |  | 2020-06-18 | 2020-06-20 | 3 | Complete
| Featuredesign transfer employee page |  | Bayan |  | 2020-06-21 | 2020-06-24 | 4 | Overdue
| Sprint 2 |  | Bayan &Sleman |  | 2020-06-25 | 2020-07-05 | 12 | In Progress
| design transfer page at the same city |  | Bayan |  | 2020-06-25 | 2020-06-28 | 4 | In Progress
| design transfer page between two citie |  | Bayan |  | 2020-06-29 | 2020-07-01 | 4 | Not Started
| make mysql database |  | Sleman |  | 2020-07-02 | 2020-07-05 | 4 | Not Started
| Sprint 3 |  | Alin &Tamara |  | 2020-07-06 | 2020-07-17 | 12 | Not Started
| make backend api |  | Tamara |  | 2020-07-06 | 2020-07-08 | 3 | Not Started
| connect Backend with frontend |  | Tamara & Alin |  | 2020-07-09 | 2020-07-10 | 2 | Not Started
| Test the App |  | Alin |  | 2020-07-11 | 2020-07-17 | 7 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.